## Slide 1: DANANG BUS ROUTES FINDER “DANABUS"
Group member:
Lê Trọng Hiếu
Nguyễn Định An
Trương Thị Vân Anh
Trần Viết Anh Quốc

## Slide 2
1
Project Overview
5
Quality Management
3
Project Start-up
7
References
Section 1. Project Overview
2/46
4
Monitoring and Control
8
Glossary
2
Project Organization
6
Project Transition

## Slide 3
A
Project Description
C
Project Scope
3/46
B
Assumptions
D
Constraints
Section 1. Project Overview

## Slide 4
Danang Government
Danang Department of Transportation
Danang ICT Infrastructure Development Center
AHAQ High Tech Software Ltd.
Stakeholder
4/46
Section 1. Project Overview

## Slide 5
Citizens are still not really impressed by public transport systems
Environmental pollution, noise pollution, traffic jams, traffic accidents, etc…
Need a solution to enhance the number of bus users
Problem
Section 1. Project Overview

## Slide 6
Help users know detailed information about bus.
Find the optimal route from starting point and end point.
“Danabus” Application
6/46
Section 1. Project Overview

## Slide 7
Application: run on mobile devices only, iOS 9.0 or above, Android 5.0 or above
Language: Vietnamese & English
Connection: Internet & GPS
Project Scope
7/46
Main features:
    Find routes
Estimate waiting time
Look up information,
Find bus stop
Update data
Feedback
Section 1. Project Overview

## Slide 8
Resource Assumptions
Technology assumptions
Business assumptions
Financial assumptions
Assumptions
8/46
Schedule constraints
Scope constraints
Cost constraints
Constraints
Section 1. Project Overview

## Slide 9
A
Internal Structure
Section 2. Project Organization
9/46
B
External Stakeholders
C
Roles and Responsibilites

## Slide 10
Internal Structure
10/46
Section 2. Project Organization

## Slide 11
External Stakeholders
11/46
Stakeholder Organization | Organization Description/Nature of Relationship | Stakeholder Name
Danang Government | Agency for licensing and authorizing projects | Government
Danang DoT | Direct customer of the company | Customer
Danang IIDC | The agency provides hardware and assists the company in product deployment | Supplier
Section 2. Project Organization

## Slide 12
Roles and Responsibilities
12/46
Executive Committee
IT Director
Project Director
Project Manager
Scrum Master
Database Analyst
Business Analyst
Testing Team
Section 2. Project Organization

## Slide 13
Roles and Responsibilities
13/46
Section 2. Project Organization

## Slide 14
Roles and Responsibilities
14/46
Section 2. Project Organization

## Slide 15
A
Project Life Cycle
Section 3. Project Start-up
15/46
B
Methods, Tools, and Techniques
C
Estimation Methods
E
Schedule Allocation
F
Resource Plan
G
Budget Allocation
D
Work Activites

## Slide 16
Project Life Cycle
16/46
Devided into 6 phase
Phase 1: Conducted requirements
Phase 2: define software needs
Phase 3: Design
Phase 4: Coding
Phase 5: Installing/Deployment
Phase 6: Maintenance
Section 3. Project Start-up

## Slide 17
Method, Tools, and Techniques
17/46
System Development Standards
Documentation Standards
Program Standards
Command File Standards
Test Case Standards
Section 3. Project Start-up

## Slide 18
Estimation Methods
18/46
Description
Effort in person-months or person-hours
Schedule in calendar months
Budget in dollars
Source/Basis of Estimate
Level of Uncertainty
Section 3. Project Start-up

## Slide 19
Work Activities
19/46
Product Work Breakdown Structure
Section 3. Project Start-up

## Slide 20
Work Activities
20/46
Process Work Breakdown Structure
Section 3. Project Start-up

## Slide 21
Schedule & Budget Allocation
21/46
Section 3. Project Start-up

## Slide 22
Schedule & Budget Allocation
22/46
Chart: 
| Planning | Management | Requirements | Prototyping | Configuration management | Functional design | Design review 1 | Detail design | Design review 2 | Quality assurance | Coding | Reuse acquisition | Code inspections | Unit test | Function test | System test | Field test | User documents | Document reviews | Installation
Start date | 43101 | 43101 | 43140 | 43153 | 43169 | 43160 | 43178 | 43214 | 43255 | 43188 | 43230 | 43277 | 43400 | 43412 | 43490 | 43504 | 43570 | 43414 | 43492 | 43565
323 | 323 | 352 | 29 | 19 | 295 | 40 | 29 | 60 | 17 | 289 | 201 | 7 | 86 | 88 | 57 | 43 | 25 | 115 | 56 | 58
Section 3. Project Start-up

## Slide 23
Resource Plan
23/46
Resource profiles
Section 3. Project Start-up

## Slide 24
Resource Plan
24/46
Resource profiles
Section 3. Project Start-up

## Slide 25
Resource Plan
25/46
Resource Staffing
Section 3. Project Start-up

## Slide 26
Section 4. Monitoring and Control
26/46
C
B
Issue Management
A
Change Control
C
Status Reporting

## Slide 27
Managing a Scope Change Management.
Scope increase.
Unplanned Tasks.
Scope Decrease.
Change Request Tracking
27/46
Section 4. Monitoring and Control

## Slide 28
Change Request Tracking
28/46
Scope Change Management
Section 4. Monitoring and Control

## Slide 29
Project Renegotiation
Impact on cost and project schedule
Change Request Tracking
29/46
Section 4. Monitoring and Control

## Slide 30
Change Request Review
Role | Person | Responsibility
Project Director | Mr. Nguyen Dinh An | Initiates a change request. Reviews and approves change requests.
Project Manager |  | Initiates a Change Request. Analyze the impact. Creates and maintains Change Requests in Clarity. Reviews and obtains approval. Project scope management Maintains the project plan.
Backend Team Testing Team Frontend Tem | All member in team | Initiates a Change Request. Analyzes the impact and Implements approved Change Requests.
IT Director Scrum Master | Mr. Le Trong Hieu Ms. Truong Thi Van Anh | Reviews and approve
Project Management Office | Mr. Cao Son Duc | Review and follow up. Monitors project variances.
Section 4. Monitoring and Control

## Slide 31: Issue Management
Use “clarity issue tracking” issue tracking software.
31/46
Detailed instruction about this software will be described in another documents.

## Slide 32: Status Reporting
32/46
Field | Value
Change request ID | Business Justification
Change request Name | Entered name
Description | Summary description text
Requested by | Usually Project Manager
Status | Approved/Denied/Pending
Date | Date time
Reason | Approved/Denied reason
Comments | Other comments for clarification purpuse
Deliverables Impacted | Enter in any deliverables that will be impacted
Business Justification | Enter the business justification for the Project Change Request.

## Slide 33
Section 5. Quality Management
33/46
B
Quality Standards
A
Quality Objectives
C
Project Reviews and Assessments
D
Deliverables Acceptance
E
Prosess Improvement Activities

## Slide 34
The DanaBus Application Plan identifies three brief goal.
All of main features: find optimal bus route, find bus stop, bus schedule details, estimate waiting time and feedback must be available.
Help users get the best experience when using the bus service.
The application must meet the target of 3.5/5 stars or receive over 100 feedbacks from users on the App Store and Google Play Store.
34/46
Quality Objectives
Section 5. Quality Management

## Slide 35
35/46
No. | Quality Standards | Tracking Tools or Measures
1 | Six Sigma | Redmine, Jira, clarity issue tracking
2 | IEEE 12207-2017 – ISO/IEC/IEEE | Redmine, clarity issue tracking
3 | AHAQ Coding Convention | GitHub, Jira, clarity issue tracking
Quality Standards
Section 5. Quality Management

## Slide 36
36/46
Review Type | Quality Standard | Tools | Reviewer | Reports
Project Report | Six Sigma | Redmine Jira clarity issue tracking | IT Director Project Director Executive Committee Project Manager Stakeholders | Review Report
Project Audit | Six Sigma | Redmine Jira | Business Analyst Project Manager Project Director Executive Committee | Audit Report
Daily Review | AHAQ Coding Convention | GitHub Jira clarity issue tracking | Backend Team Frontend Team Testing Team Database Analyst Project Manager Scrum Master IT Director | Individual Report
Quality Review | Six Sigma | Redmine Jira clarity issue tracking | Testing Team Business Analyst Project Manager Scrum Master Project Director | Quality Report
Project Reviews and Assessments

## Slide 37
37/46
Deliverable | Fimal Approval Process | Customer Acceptance Criteria
Requirements document | Requirements | The requirements that customer give are fully described.
Design drawings and documents | Design review 1 Design review 2 Detail Design | - Design and documents that meet the requirements. - Customer satisfy about UI pattern.
Project plan | Planning Management | - The stages are properly deployed. - The budget does not exceed the allowable level. - Products are delivered on given time.
Product prototype | Prototyping | The prototype is standardized with design.
Beta version application “DanaBus” | Installation Deployment | All of main features must be available.
Completed application “DanaBus” | Installation Deployment | - All of main features must be available. - The product operates smoothly and there are no major errors.
User document | User document | - Full description of the application. - Future maintenance and development capabilities
Deliverables Acceptance

## Slide 38
Participants: IT Director, Project Director, Executive Committee, Project Manager, Stakeholders.
Activities: Often a monthly status report is provided to the stakeholder and executive committee as an update of employee’s plans and activities.
Goal: Provides a higher-level view of the developments in the project.
Project Monthly Report
38/46
Section 5. Quality Management

## Slide 39
Participants: Project Manager, Backend Team, Frontend Team, Testing Team, Database Analyst, Business Analyst, IT Director
Activities: Discuss and review the day's work among members.
Goal: Identify issues, ability to complete tasks and propose methods to complete each stage of the project.
Daily Review
39/46
Section 5. Quality Management

## Slide 40: Section 6. Project Transition
Include 3 phases:
Phase 1: Create all the needed document about this project (including Project Close Out Report).
Phase 2: Handover the management process to city’s departement of transport.
Phase 3: The whole team is in “waiting state” for maintenance purposes.
Closeout Plan
40/46

## Slide 41
The current contract between our company and city’s government is lasting 5 years. So Phase 2 will close after 5 years if there are no new renew contract request from the customer.
Phase Closeout
41/46
Section 6. Project Transition

## Slide 42: Section 7. References
42/46
Document No. | Document Title | Date | Author
1 | Information Technology Project Management 6th | 2011 | Kathy Schwalbe
2 | Project Structure and Organisation | N/A | N/A
3 | What is PERT and how can we use it? | 2015 | Dave Fourie
4 | V-model wiki | 2019 | N/A
5 | Oakland County Department of Information Technology | N/A | Oakland County Department of Information Technology

## Slide 43: Section 8. Glossary
43/46
Abbreviation | 
DoT | Department of Transportation
Danang IIDC | Danang ICT Infrastructure Development Center
SDLC | Software Development Life Cycle
PERT | Project Evaluation and Review Technique
FTE | Full-Time Employed
TMF | Toyota Mobility Foundation

## Slide 44: Section 8. Glossary
44/46
Glossary | 
Assumption | Factors deemed to be true during the project planning process, though proof of their validity is not available.
Baseline | This term represent the costs and schedules approved at the start of the project.
Budget | The sum of money allocated for a project
Change control | Change control is the process of identifying, evaluating, approving, and implementing changes to a project.
Change management plan | It is created to ensure all changes are managed according to procedure.
Critical path activity | A scheduled activity that is part of a project’s critical path.

## Slide 45: Section 9. Revision History
45/46
Version | Date | Name | Description
1st | 2019, March 15th | Project Initiation | Identify project scope, assumption, constraints,...
2nd | 2019, April 12th | Project Start | Complete Project Plan